PROCESS SUMMARY GUIDE

From LinkedIn Profiles to Executive Dashboard — A Complete AI-Assisted PM Workflow

Course: PMI Course — Generative AI for Project Managers

Institution: Hochschule Harz (HS Harz)

Project: Automotive Airbag ECU Functional Safety Simulation System

Project Manager: Alita Shrestha

Date: June 2026

| 📖 WHO IS THIS FOR? | This document is for anyone who is new to using AI tools in project management and wants to understand, step by step, how this entire body of work was produced. You do not need a technical background. By the end, you will understand what was built, how it was built, and how to reproduce a similar workflow for your own projects. |
| --- | --- |

# 1. Overview — What We Built and Why

This project used Generative AI (specifically, Anthropic Claude) to complete a full project management skills analysis workflow — the kind of work that would normally take a team of consultants several weeks. It was completed in a single session, using only natural language instructions (no coding required from the user).

The starting point was simple: eleven PDF files containing LinkedIn profiles of team members, and a project charter PDF describing an upcoming engineering project. The end result was six professional deliverables — two interactive web dashboards and four Word documents — covering everything from team skills tracking to executive reporting.

## 1.1  The Deliverables — At a Glance

| Talent_Skills_Registry.xlsx | Excel | A structured database of all 11 team members — their roles, skills, proficiency levels, years of experience, education, and certifications. The single source of truth for all team capability data. |
| --- | --- | --- |

| Team_Skills_Dashboard.html | Dashboard | An interactive visual dashboard showing team skills across 8 domains, with drill-down by category, individual vs. team comparisons, and a skills heatmap. Open in any browser. |
| --- | --- | --- |

| Airbag_ECU_Skills_Competencies.docx | Word | 44 required skills for the project, organised by domain, with priority ratings (Critical / High / Medium / Low), proficiency requirements, and the responsible roles. Derived from the project charter. |
| --- | --- | --- |

| Airbag_ECU_Gap_Analysis.docx | Word | A structured comparison of what the team can currently do versus what the project needs. Includes role-by-role coverage assessment, domain gap scores, and a 10-point action plan. |
| --- | --- | --- |

| Airbag_ECU_Training_Plan.docx | Word | 40+ specific learning resources (courses, books, free tools) for every skill gap — with providers, costs, durations, and direct URLs. Includes a budget estimate and role-specific learning paths. |
| --- | --- | --- |

| Skills_Gap_Executive_Dashboard.html | Dashboard | A jargon-free interactive dashboard for senior stakeholders. 8 KPI cards, visual role coverage, team member assessments, priority action cards, and a training investment breakdown. |
| --- | --- | --- |

| 💡 KEY INSIGHT | None of these deliverables required writing code, manual data entry, or formatting documents by hand. Every file was generated by giving Claude natural language instructions — the same way you would ask a knowledgeable colleague to help you. |
| --- | --- |

# 2. The Process — Step by Step

The workflow unfolded in eleven distinct steps. Each step built on the previous one. Here is exactly what happened, why each step mattered, and what was produced.

| STEP 1 | Creating the Skills Template Building the foundation — an empty spreadsheet structure to hold team data |
| --- | --- |

| WHAT | We asked Claude to create a blank Excel spreadsheet template with columns for Name, Skills, Proficiency Level, Years of Experience, Education, and Certifications. |
| --- | --- |
| WHY | Before collecting any data, you need to decide what data to collect and how to structure it. A consistent template ensures that information from 11 different people can be compared fairly — like standardising a form before handing it out. |
| HOW | Claude generated a Python script using the openpyxl library to create the Excel file with formatted headers, colour-coded proficiency badges (Expert, Advanced, Intermediate, Beginner), frozen header rows, and a legend. The script was run in a sandboxed Linux environment. |
| RESULT | File: Talent_Skills_Registry.xlsx (blank template with structure and formatting ready to receive data) |

| 📝 BEGINNER NOTE | openpyxl is a Python library that can create and edit Excel files without needing Excel installed. Think of it as a robot that builds spreadsheets. Claude wrote the robot instructions (the code) and ran them — we just described what we wanted. |
| --- | --- |

| STEP 2 | Extracting Data from LinkedIn Profile PDFs Reading 11 PDF files automatically — no copy-pasting |
| --- | --- |

| WHAT | We asked Claude to access a folder containing 11 LinkedIn profile PDFs (named Profile.pdf through Profile (10).pdf) and extract the relevant information from each one. |
| --- | --- |
| WHY | Manually reading 11 profiles, deciding what information matters, and typing it all into a spreadsheet is slow and error-prone. AI can read PDF text in seconds, identify the relevant fields, and structure the information consistently — a task that would take a human hour takes AI seconds. |
| HOW | Claude installed the pdfplumber Python library and wrote a script to open each PDF, extract all text, and print it to the screen. The text was then analysed by Claude to identify each person's role, skills, experience level, education, and certifications. |
| RESULT | All 11 profiles were successfully read. The raw text from each was available for the next step — data normalisation and population of the spreadsheet. |

| 📝 BEGINNER NOTE | PDF files contain text in a format that is hard for machines to read directly. pdfplumber is a Python library that extracts the raw text from PDF pages. Once Claude had the text, it could read it like a human would — understanding context, inferring meaning, and identifying relevant information. |
| --- | --- |

| STEP 3 | Populating the Talent Registry Turning raw LinkedIn data into a structured, comparable database |
| --- | --- |

| WHAT | We asked Claude — acting as an expert project manager — to analyse all 11 LinkedIn profiles, normalise the data, and populate the talent registry spreadsheet with structured, comparable information. |
| --- | --- |
| WHY | Raw LinkedIn profiles are not structured data. Each person describes their skills differently. Normalisation means applying a consistent framework — the same proficiency scale, the same skill categories, the same experience measurement — so that everyone can be compared fairly. This is a judgement-intensive task where AI adds real value. |
| HOW | Claude read all 11 profile texts, inferred each person's proficiency level (Expert / Advanced / Intermediate / Beginner) based on their years of experience and described responsibilities, identified their top skills, and wrote a Python script using openpyxl to insert the data into the spreadsheet with appropriate formatting. |
| RESULT | File: Talent_Skills_Registry.xlsx (fully populated with 11 team members, colour-coded proficiency levels, and a proficiency legend) |

| 💡 KEY INSIGHT | Normalisation is one of the most valuable things AI can do with unstructured data. The AI did not just copy text from PDFs — it interpreted experience levels, inferred skill categories, and applied a consistent professional judgement framework across all 11 profiles simultaneously. |
| --- | --- |

| STEP 4 | Creating the Interactive Skills Dashboard Visualising team skills so patterns become obvious at a glance |
| --- | --- |

| WHAT | We asked Claude to create an interactive data visualisation showing the team's collective skills and experience, with the ability to identify areas of strength and opportunities for development. |
| --- | --- |
| WHY | Raw data in a spreadsheet is hard to interpret quickly. A visual dashboard transforms numbers into patterns that are immediately meaningful — you can see at a glance which skill domains are strong, which are weak, which team members are specialists, and how experience is distributed. Dashboards make decisions faster and better. |
| HOW | Claude designed a standalone HTML file using Chart.js (a free JavaScript charting library) with a donut chart for proficiency distribution, a radar chart for individual vs. team comparisons, a horizontal bar chart for experience, clickable domain bars, a heatmap, and a bubble chart. All charts are interactive. |
| RESULT | File: Team_Skills_Dashboard.html (a standalone HTML page that runs in any browser with no installation required) |

| 📝 BEGINNER NOTE | HTML (HyperText Markup Language) is the language web pages are written in. A standalone HTML file is a complete webpage saved as a single file on your computer — you open it by double-clicking it, just like a Word document. Chart.js is a free library that draws interactive charts inside webpages. |
| --- | --- |

| STEP 5 | Anonymising Team Member Names Protecting team members' privacy before sharing |
| --- | --- |

| WHAT | We asked Claude to replace all real team member names with random-sounding fictional names, keeping all other data identical, and recreate the dashboard with the anonymised names. |
| --- | --- |
| WHY | Professional practice requires protecting individual privacy when sharing team data with people outside the immediate project group. By replacing real names with fictional ones, the dashboard can be shared with stakeholders, uploaded to GitHub, or used for teaching purposes without identifying individuals. |
| HOW | Claude generated 11 realistic-sounding fictional names (e.g., Maya Torres, Sofia Brennan, Lucas Chen) and updated both the spreadsheet and the dashboard code. The anonymised names were used consistently across all subsequent documents. |
| RESULT | All documents and dashboards in this repository use anonymised names. The mapping between real and fictional names is kept separately in the project's internal records. |

| STEP 6 | Enhancing the Dashboard with Advanced Features Adding drill-down, tooltips, heatmap, and insights |
| --- | --- |

| WHAT | We asked Claude to add more interactive features: drill-down into skill categories, individual vs. team proficiency comparisons, tooltips providing context, a skills heatmap, a bubble chart, and AI-generated insight cards. |
| --- | --- |
| WHY | The first version of the dashboard showed high-level patterns. The enhanced version allows users to ask "why?" — clicking a domain bar shows which team members are strong or weak in that area. The heatmap shows the full picture at once. The insight cards surface what the data means, not just what it shows. |
| HOW | Claude rewrote the dashboard with Chart.js instance management (to avoid canvas reuse errors), added a dark/light mode using CSS media queries, implemented floating tooltip divs, built the heatmap as an HTML table with colour-coded cells, and programmed the AI insight cards to automatically identify the team's top strength, concentration risk, and development priority. |
| RESULT | File: Team_Skills_Dashboard.html (final enhanced version with all interactive features) |

| 📝 BEGINNER NOTE | When Claude says it "rewrote" the dashboard, it means it rewrote the code — the set of instructions that tells the browser how to draw the charts and respond to clicks. From the user's perspective, the improvement was just asking "please add these features" in plain language. |
| --- | --- |

| STEP 7 | Analysing the Project Charter PDF Extracting what the project actually needs from the official documentation |
| --- | --- |

| WHAT | We uploaded the Airbag ECU Project Charter PDF and asked Claude to review it and generate a comprehensive list of required skills and competencies for the project. |
| --- | --- |
| WHY | Before comparing the team against the project, you need to know precisely what the project demands. The project charter is the official document that defines the project's scope, deliverables, safety requirements, and team roles. Reading it carefully and extracting structured requirements is typically a time-consuming consultant task. |
| HOW | Claude used pdfplumber again to extract all 5 pages of the charter, then read and analysed the technical content — identifying safety standards (ISO 26262, IEC 61508), hardware requirements (ARM Cortex-M3, CAN Bus, 2oo2 architecture), software modules, testing requirements (MC/DC, code coverage), and all 14 formal team roles. |
| RESULT | The charter content was fully understood and held in memory for use across all subsequent documents. No separate file was created at this stage. |

| 💡 KEY INSIGHT | A 5-page technical document covering automotive safety standards, microcontroller architecture, and firmware testing methodology was fully analysed in seconds. Claude was able to understand not just what the words said, but what they implied — which skills, which roles, which training would be needed. This is the core value of a large language model applied to complex technical documents. |
| --- | --- |

| STEP 8 | Creating the Required Skills Document Building a structured, prioritised competency framework from scratch |
| --- | --- |

| WHAT | We asked Claude to generate a comprehensive Word document listing all skills and competencies required by the project, organised by domain, with priority ratings, proficiency requirements, and role mappings. |
| --- | --- |
| WHY | Project managers need a clear, structured record of what a project demands — not just for planning, but for team selection, training investment decisions, and audit purposes. Converting a technical project charter into a readable, prioritised competency framework is exactly the kind of analysis work that takes experienced professionals days. |
| HOW | Claude structured 44 skills into 8 domains, assigned each a priority (Critical / High / Medium / Low) and a minimum proficiency level, and mapped each to the responsible charter role(s). It then generated a Node.js script using the docx library to produce a formatted Word document with colour-coded tables, headers, and a professional layout. |
| RESULT | File: Airbag_ECU_Skills_Competencies.docx (44 skills across 8 domains with priority ratings, proficiency requirements, role mappings, gap identification guidance, and competency confirmation requirements) |

| 📝 BEGINNER NOTE | The docx library is a Node.js package (Node.js is a JavaScript runtime — JavaScript is the language web browsers use). Claude wrote JavaScript code that describes every paragraph, table cell, colour, and font in the Word document programmatically. The output is a real .docx file that Word can open and edit. |
| --- | --- |

| STEP 9 | Performing the Gap Analysis Comparing what the team has against what the project needs |
| --- | --- |

| WHAT | We asked Claude to produce a detailed gap analysis comparing the current team's skills (from the LinkedIn dashboard data) against the 44 required project skills, presented as a colour-coded Word document. |
| --- | --- |
| WHY | Knowing what you need (Step 8) and knowing what you have (Steps 2–4) is only useful once you compare them. A gap analysis surfaces the specific differences — which roles are filled, which are partially filled, which are empty, and how large each capability deficit is. This is the document that drives resource planning and training investment decisions. |
| HOW | Claude mapped each of the 14 charter roles to the best available team member, scored each domain gap on a 0–3 scale, rated overall fit (Strong / Partial / Weak / None), identified 3 team members as misaligned with the project's needs, and generated a 10-point priority action plan. The result was built as a structured Word document with colour-coded tables. |
| RESULT | File: Airbag_ECU_Gap_Analysis.docx (role mapping for all 14 roles, domain gap scores, individual member assessments, misalignment identification for 3 members, and a prioritised action plan) |

| ⚠ KEY FINDING | 4 of 14 required roles had no qualified candidate in the existing team. 0% of team members had any formal training in the international safety standards the project must comply with. These findings would have taken an experienced HR consultant several days of interviews and analysis to surface. The AI produced them in minutes — drawing on the LinkedIn data, the charter analysis, and professional knowledge of functional safety requirements. |
| --- | --- |

| STEP 10 | Building the Training Plan Prescribing exactly what to learn, where to learn it, and what it costs |
| --- | --- |

| WHAT | We asked Claude to create a training plan with specific learning resources for each skill gap — real courses from real providers, with costs, durations, and direct links — along with role-specific learning paths and a budget estimate. |
| --- | --- |
| WHY | A gap analysis tells you what is missing. A training plan tells you what to do about it. The difference between a generic recommendation ("they need training") and a specific one ("here is the exact Exida 2-day ISO 26262 Foundation course at €700 that Dev Okafor should attend before Week 3") is the difference between a document that gets filed and one that drives action. |
| HOW | Claude drew on its training knowledge of specific education providers (Exida, TÜV SÜD, Vector Academy, Kvaser, Coursera, Udemy, IREB, ISTQB), cross-referenced them with each team member's specific gap, sequenced the learning for each person, and produced the output as a detailed Word document with provider tables, role-specific learning paths, and a full budget table. |
| RESULT | File: Airbag_ECU_Training_Plan.docx (40+ specific resources across 9 skill areas, 8 role-specific learning paths, 15 free resources listed separately, budget estimate of €3,500–€6,500 for team training) |

| STEP 11 | Creating the Executive Dashboard Translating technical findings into language any stakeholder can understand |
| --- | --- |

| WHAT | We asked Claude to create an interactive HTML dashboard for senior executives that visualises the skill gap analysis and training plan findings in a jargon-free, engaging, and visually clear format. |
| --- | --- |
| WHY | The Word documents produced in Steps 8–10 are thorough and professional — but they are designed for project managers and technical leads who read long documents. Senior executives need to absorb the same information in 5 minutes: what is the risk, how bad is it, what needs to happen, and what does it cost. A well-designed dashboard communicates this faster than any report. |
| HOW | Claude designed a standalone HTML dashboard with 8 KPI cards, a role coverage donut chart, domain gap stacked bars, 14 clickable role cards, 11 team member profile cards, a 3-column priority action plan, a training investment table, and a 12-term glossary. Every technical term has a hover tooltip explaining it in plain language. The design uses a professional navy-and-white colour scheme with red/amber/green traffic-light coding throughout. |
| RESULT | File: Skills_Gap_Executive_Dashboard.html (single standalone HTML file, opens in any browser, no installation required, fully interactive with tooltips and clickable elements) |

| 💡 KEY INSIGHT | The executive dashboard was designed around a specific principle: a C-suite executive who has never heard of ISO 26262 or ASIL D should be able to open this page and, within 5 minutes, understand that (1) 4 critical roles have no qualified person, (2) the biggest risk is the complete absence of safety standards knowledge, (3) an external Safety Manager must be hired immediately, and (4) the total investment required is approximately €13,000–€47,000. The technical details are available via tooltips and drill-down for those who want them. |
| --- | --- |

3. How Everything Connects

Each deliverable in this project feeds into the next. The diagram below (described as a table since Word cannot render diagrams programmatically) shows the data flow:

| 11 LinkedIn Profile PDFs | → | Talent Skills Registry (Excel) | → | Team Skills Dashboard (HTML) | + | Project Charter PDF |
| --- | --- | --- | --- | --- | --- | --- |

| "What does the team have?" | + | "What does the project need?" |
| --- | --- | --- |

|  | GAP ANALYSIS (Word) |  |
| --- | --- | --- |

| Required Skills Document (Word) | → | Training Plan (Word) | → | Executive Dashboard (HTML) |
| --- | --- | --- | --- | --- |

# 4. What the AI Did — And What You Did

A common question about AI-assisted workflows is: "How much did you actually do, versus the AI?" Here is an honest breakdown:

| What the AI (Claude) did | What the project manager (you) did |
| --- | --- |
| Read and extracted text from 14 PDF files | Decided what questions to ask and in what order |
| Interpreted and normalised 11 LinkedIn profiles | Provided the source materials (PDFs) |
| Wrote all Python, JavaScript, and HTML code | Reviewed outputs and directed refinements |
| Designed and formatted all six documents | Chose the output format (Word vs. HTML) |
| Identified 44 required skills from the charter | Determined the scope of each analysis |
| Mapped team capabilities to project requirements | Set the budget framing (mixed budget approach) |
| Researched and selected specific training providers | Decided what tone to strike for the executive audience |
| Wrote all analysis, recommendations, and explanations | Gave feedback that improved each output ("make it more visual", "add tooltips") |

| 💡 KEY INSIGHT | The project manager's role in an AI-assisted workflow shifts from doing the work to directing the work. You need to know what good output looks like, what questions to ask, and when to push for more detail or a different approach. The AI does the production — you do the thinking about what needs to be produced. |
| --- | --- |

# 5. Tools and Technologies Used

You do not need to understand these tools to use the deliverables. This section is for anyone who wants to understand how they work or replicate this workflow.

| Tool | Category | What it was used for |
| --- | --- | --- |
| Anthropic Claude | AI Assistant | Everything — data extraction, analysis, code writing, document creation, and dashboard design. All work was directed through natural language conversation. |
| Python | Programming Language | Used to read PDF files (pdfplumber library) and create/populate the Excel spreadsheet (openpyxl library). Claude wrote all the Python code. |
| pdfplumber | Python Library | Extracts raw text from PDF files. Used to read the 11 LinkedIn profiles and the 5-page project charter. |
| openpyxl | Python Library | Creates and edits Excel files (.xlsx) without needing Excel installed. Used to build the Talent Skills Registry with formatting, colours, and a proficiency legend. |
| Node.js | JavaScript Runtime | Runs JavaScript code outside of a browser. Used to execute the document-building scripts. |
| docx (npm library) | JavaScript Library | Creates Word documents (.docx) programmatically. Claude used this to generate all three Word documents with tables, colours, and professional formatting. |
| HTML / CSS / JavaScript | Web Technologies | The standard languages for building web pages. Both dashboards are HTML files — Claude wrote all the HTML, CSS (styling), and JavaScript (interactivity) code. |
| Chart.js 4.4.1 | JavaScript Library | A free, open-source library for drawing interactive charts (donut, radar, bar, bubble) inside webpages. Used in both dashboards. |
| Google Fonts (Inter) | Typography CDN | The Inter typeface used in both dashboards, loaded from Google's free font service for a clean, modern appearance. |

# 6. How to Replicate This Workflow for Your Own Project

This workflow can be adapted for any project where you need to assess team skills against project requirements. Here is a simplified guide:

## 6.1  What You Need to Start

- Team members' profiles (LinkedIn PDFs, CVs, or even a simple list of roles and skills)

- A project document (charter, scope statement, or requirements list) that defines what skills the project needs

- Access to an AI assistant (Claude, ChatGPT, or similar) — a web browser is all that is required

## 6.2  The Conversation Pattern

The most important skill in an AI-assisted workflow is knowing how to ask. Here is the pattern used throughout this project:

| Instruction Type | Example |
| --- | --- |
| Set the role | "You are an expert project manager working on skills and performance tracking..." |
| Describe the input | "Study the LinkedIn profile information in those 11 PDF files..." |
| Describe the output | "...aggregate and normalise the data into the talent and skills spreadsheet template you created" |
| Specify the format | "Create this as a standalone HTML file with proper CSS so that I can share it with others" |
| Iterate and refine | "Please add tooltips, a heatmap, and drill-down by skill category" |

## 6.3  Tips for Getting Better Results

- Be specific about who will use the output ("this is for senior executives who are not technical") — it changes the language and design significantly.

- Ask for one thing at a time for complex outputs. Build the template first, then populate it, then visualise it.

- When the AI produces something close but not quite right, describe the change specifically ("make the gap bars show the percentage as a label inside the bar") rather than asking it to start again.

- Ask the AI to explain what it is doing if you are learning. It will describe each tool and decision as it works.

- If a document is too technical, ask explicitly: "Remove jargon and explain this for a non-technical audience." The same content can be re-written at any level.

- The AI keeps context from the conversation. You can say "use the same colour scheme as the previous dashboard" and it will apply it without re-specification.

# 7. Key Lessons from This Workflow

Reflecting on the full process, these are the most important observations for any project manager considering a similar approach:

## 7.1  What AI Does Exceptionally Well in PM Workflows

- Reading and structuring unstructured data — PDFs, emails, meeting notes — into consistent, comparable formats.

- Finding patterns and making comparisons across large amounts of information (11 profiles, 44 skills, 14 roles) simultaneously.

- Producing professional-quality documents and code without formatting time or technical barriers.

- Translating the same analysis for different audiences (technical report vs. executive dashboard) without duplicating work.

- Researching specific options (real training courses, real providers, real costs) and synthesising them into a structured plan.

## 7.2  What the Project Manager Still Needs to Do

- Make the judgement calls — which skills matter most, what the priority order should be, what the budget limits are.

- Know what good looks like — you need to be able to review the output critically, not just accept it.

- Provide the source materials — the AI needs good input to produce good output. Garbage in, garbage out still applies.

- Take accountability — the AI's analysis is a starting point, not a final answer. The PM must validate findings against their own knowledge of the team and context.

- Decide when to stop — there is always another visualisation, another analysis, another document. Knowing when the work is complete is a human judgement.

## 7.3  Limitations to Be Aware Of

- AI can misread poorly structured PDFs. Always check extracted data against the source.

- AI's cost and course information may be slightly outdated. Always verify current prices and availability directly with providers.

- AI cannot replace domain expertise. The functional safety analysis in this project relies on the AI's trained knowledge — a certified safety professional should validate any safety-critical decisions.

- AI-generated code works but may not follow every software best practice. For production systems, have a developer review the code.

# 8. Complete Deliverables Summary

Everything produced in this workflow, with a one-line description of how to use each item:

| File | Format | How to use it |
| --- | --- | --- |
| Talent_Skills_Registry.xlsx | Excel | Open in Excel or Google Sheets. Filter by proficiency level or skill to identify candidates for specific roles. Update as team members develop. |
| Team_Skills_Dashboard.html | Browser | Double-click to open in any browser. Click domain bars to drill down. Click team member names to compare against the team average. Use the heatmap to spot coverage gaps. |
| Airbag_ECU_Skills_Competencies.docx | Word | Reference document for team selection, role assignment, and training investment decisions. Filter by "CRITICAL" priority to identify the highest-stakes skills. |
| Airbag_ECU_Gap_Analysis.docx | Word | The primary decision-support document. Use the role mapping table to understand resourcing needs and the action plan to prioritise interventions. |
| Airbag_ECU_Training_Plan.docx | Word | Hand the role-specific learning paths to individual team members as their personal development plan. Use the budget table for procurement approvals. |
| Skills_Gap_Executive_Dashboard.html | Browser | Open in a browser for presentations to senior management. Hover over underlined terms for plain-language explanations. Click role cards for individual assessments. |
| Process_Summary_Guide.docx (this document) | Word | Share with anyone new to this process who wants to understand how the workflow was designed and how to replicate it for their own project. |
| README.md | Markdown | The front page of the GitHub repository. Describes every file, provides quick-start instructions, and gives a project overview for anyone finding the repository. |

| 🎓 FINAL NOTE | This entire workflow — from blank spreadsheet template to executive dashboard — was completed in a single project management session. The AI handled all technical production. The project manager handled direction, judgement, and quality control. This is the future of project management: not replacing the PM, but dramatically expanding what one PM can produce. |
| --- | --- |